## Sheet1
METERIQ — SMART METER ANALYTICS
[MeterIQ Project Team] |  | Project Start: | 2026-08-25
[Project Lead] |  | Today: | 2026-09-15
|  | Display Week: | 4 |  | 2026-08-25 | [6 empty] | 2026-09-01 | [6 empty] | 2026-09-08
[5 empty] | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15
TASK | ASSIGNED TO | PROGRESS | START | END | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
Phase 1 — Requirements & System Design
Problem Statement & Requirements | Yashit + Aarushi | 100% | 2026-08-25 | 2026-08-26
Use Case Diagram | Yashit | 100% | 2026-08-25 | 2026-08-25
DFD Level 0, 1 & 2 | Aarushi | 100% | 2026-08-25 | 2026-08-29
ER Diagram | Aarushi | 100% | 2026-09-08 | 2026-09-11
Activity Diagram | Yashit + Aarushi | 100% | 2026-09-08 | 2026-09-11
Phase 2 — Dataset & Data Preparation
Dataset Understanding | Yashit + Aarushi | 100% | 2026-08-29 | 2026-09-01
Exploratory Data Analysis (EDA) | Aarushi | 100% | 2026-08-29 | 2026-09-05
Data Preprocessing | Aarushi | 100% | 2026-09-01 | 2026-09-08
Feature Engineering | Aarushi | 100% | 2026-09-01 | 2026-09-08
Prepared Dataset Validation | Yashit + Aarushi | 0% | 2026-09-20 | 2026-09-21
Phase 3 — Machine Learning
Anomaly / Risk Detection | Yashit + Aarushi | 0% | 2026-09-22 | 2026-09-28
Short-Term Load Forecasting | Yashit + Aarushi | 0% | 2026-09-22 | 2026-09-28
Model Evaluation | Yashit + Aarushi | 0% | 2026-09-29 | 2026-10-02
Explainability Analysis | Yashit + Aarushi | 0% | 2026-10-03 | 2026-10-05
ML Output Preparation | Yashit + Aarushi | 0% | 2026-10-06 | 2026-10-07
Phase 4 — Dashboard & System Integration
React Dashboard Development | Yashit | 100% | 2026-09-05 | 2026-09-11
Backend/API Development | Yashit + Aarushi | 0% | 2026-10-08 | 2026-10-14
ML + Backend Integration | Yashit + Aarushi | 0% | 2026-10-15 | 2026-10-19
Dashboard + ML Integration | Yashit | 0% | 2026-10-20 | 2026-10-23
System Testing & Bug Fixing | Yashit + Aarushi | 0% | 2026-10-24 | 2026-10-28
Phase 5 — Documentation & Submission
Project Proposal | Yashit + Aarushi | 0% | 2026-10-01 | 2026-10-05
Gantt Chart | Yashit + Aarushi | 100% | 2026-09-15 | 2026-09-15
Weekly Journals | Yashit + Aarushi | 75% | 2026-08-25 | 2026-10-30
LaTeX Project Report | Yashit | 25% | 2026-09-08 | 2026-09-15
Final PPT / PDF & GitHub Submission | Yashit + Aarushi | 0% | 2026-10-29 | 2026-10-31